Name of Program: HR at State Level.

FMR Code: …A.10.1.11.1………………….

- Current Status & Situation Analysis:   Approval for programme management staff is being granted in NHM at divisional level. There are RPM, RAM, RM&EO, BME, HMIS-SUPERVISOR, RADIATION SAFETY OFFICER, ACCOUNTANT, ACCOUNT ASSISTANT AND OFFICE ASSISTANT is proposed and placed.

- Goals: To Strengthen NHM implementation at divisional level.

- Objective:

- To manage all NHM programme in the districts falling under the division.

- To provide technical advice and supportive supervision in the districts falling under the division.

- To analyze physical report and financial report in the districts falling under the division.

- Targets: 1 Post each

- Strategies and Activity Proposed:

- Monthly supportive supervision cum hand holding support visits.

- Coordination with DHS including line departments and district administration for smooth implementation of the programme.

- Collection, Compilation and Analysis of district data and submission of reports to the SHSB as per need.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): One RPM, one RAM, 1 RM&EO, 1 DAC is placed in RPMU Bhagalpur. The position of HMIS supervisor, office assistance, radiation and safety officer, bio-medical engineer and accountant is vacant in RPMU Bhagalpur.

- Justification: It is an important unit of NHM for effective management of NHM programme at regional level. It is an apex body of all block and district level societies implementing NHM initiatives as well as strong supportive supervision unit for on-spot hand holding support to the block and district team in effective implementation of NHM.

- Deliverables: Strengthen block and district health societies for effective implementation and monitoring on NHM programs.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| RPM | 1 | 56760 | 681120 | B.10.1.11.1 |
| RAM | 1 | 46200 | 554400 | B.10.1.11.1 |
| RM&EO | 1 | 39600 | 475200 | B.10.1.11.1 |
| BME | 1 | 30000 | 360000 | B.10.1.11.1 |
| HMIS-Supervisor | 1 | 19800 | 237600 | B.10.1.11.1 |
| Radiation Safety Officer | 1 | 30000 | 360000 | B.10.1.11.1 |
| Accountant | 1 | 15000 | 180000 | B.10.1.11.1 |
| Office Assistant | 1 | 12000 | 144000 | B.10.1.11.1 |