Name of Program: HR at State Level.

FMR Code: …B.1.1.5.1………………….

- Current Status & Situation Analysis:  A post of Divisional ASHA Coordinator has been sanctioned in the RPMU which is in Place for supportive supervision and hand holding to district and block level AHSA programme functionaries for successful implementation of ASHA initiative.

- Goals: To Strengthen the ASHA programme.

- Objective:

- To monitor the performance of the ASHA programme in the district under the division.

- To coordinate the ASHA training programme in the district and follow up for their performance improvement.

- Targets: 1 Post

- Strategies proposed: Overall supervision and strengthening of ASHA program.

- Activity Proposed:

- Supportive supervision of ASHA training module 5, 6 & 7 & to coordinate the District trainer agency.

- Monthly supportive supervision visits on VHSND and ASHA day.

- Coordination with PRIs, Line Depts., District Administration and health officials for smooth implementation of the programme.

- Analysis of district performance and submission of reports to the SHSB.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): ASHA Module 5, 6 & 7 training 1st phase & 2nd phase completed in Division and the 3rd & 4th batch start is proposed to start in Jan’14.  HBNC Training of ASHA Facilitator is completed in the division.

- Justification: ASHA programme is an important component of NHM to for effective mobilization of the community to enhance accessibility of delivered all types of health services in the public health facilities.

- Deliverables: Community aware about their health entitlements.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  | 1 | 29700 per month | 356400 | B.1.1.5.1 |