REGIONAL HEALTH ACTION PLAN

(RPMU TIRHUT), Muzaffarpur

2014-2017

RPMU – Tirhut

Muzaffarpur

Foreword

Aknowledgment

- Background

- Process of RHAP preparation

- Profile of Tirhut Division

- Health facilities at a glance

- About RPMU

- Part A: FMR codes

- Part B.FMR codes

- Budget Excel sheet

Table of contents

Foreword

The National Rural Health Mission ( was launched in 2005 and RPMUs are established at the Divisonal level; in the year 2010-11 and  during the period 2010-11 to 2013 -14 , RPMU prepared a Regional Health Action Plan ever year . Regional Health Action Plan (RHAP) is an integral part of National Rural Health Mission. Regional Health Action Plan is critical for achieving decentralization, interdepartmental convergence, capacity building of health system and most importantly facilitating people’s participation in health programme. Regional Health Action Plan provides opportunity and space to creatively design and utilize various NRHM initiatives such as flexi –financing, Rogi Kalyan Samiti, Village Health and Sanitation Committee to achieve our goals in the division.

RHAP seeks to achieve pooling of financial and human resources allotted through various central and state programme by bringing in a convergent and comprehensive action plan at the divisional level. Recognizing the importance of Health in the process of economic and social development and improving quality of life of our citizens, Government of India has resolved to launch National Rural Health Mission to carry out necessary architectural correction in the basic health care delivery system.

With the advent of the National Urban Health Mission in the first quarter of 2013-14 , Now the NRHM is Known as NHM ( National Health Mission ) . The National Health Mission is subsumes NRHM and NUHM . As per the instructions , this RHAP incorporates the 03 financial years Planning viz- 2014-15 ,2015-16 , 2016-17 respectively . This RHAP reflects the detailed plan for the F.Y 2014-15 and reflects the broad perspective for the  F.Y 2015-16 and 2016-17 .

.

This Regional Health Action Plan (RHAP) is one of the key instruments to achieve NHM goals. This plan is based on providing support to the districts as per their needs. After a thorough situational analysis of divisional health scenario this document has been prepared. This plan address district wise requirememnent . This RHAP has been evolved through a participatory and consultative process. The goals of the Mission are to improve the availability of and access to quality health care by people, especially for those residing in rural areas, the poor, women and children.

I need to thanks the department of Health and Family Welfare and State Health Society of Bihar for their dynamic leadership of the health sector reform programme and we look forward to a rigorous and analytic documentation of their experiences so that we can learn from them and replicate successful strategies.

I am sure that this excellent report will galvanize the leaders and administrators of the primary health care system in the division, enabling them to go into details of implementation based on lessons drawn from this study.

Dr.S.M.Mushtaque

(RDD-Tirhut)

Acknowledgement

Under the National  Health Mission (NHM) this Regional Health Action Plan (RHAP) of Tirhut divsion has been prepared. From here the situational analysis proceeds to make recommendations towards a policy on workforce management, emphasis on organizational, motivational and capacity building aspects. It recommends on existing resources as manpower and materials can be optimally utilized, critical gaps identified and addressed. It looks at the facilities at different levels can be structured and reorganized.

The commitment is to bridge the gaps in public health care delivery system, has led to the formulation of Regional Health Action Plan. The collaboration of different departments which directly or indirectly related to determinants of health will lead to betterment of health care delivery, and to make this collaboration possible actions are to be outlined in the Regional Health Action Plan.

The preparation of RHAP is done through the consultative process and efforts of all RPMU members make this plan a effective and concrete one through which we will provide guidance to all the districts in the division for effective implementation of the health programmes  in the district as per the approved PIPs.

I hope that, this Regional  Health Action Plan would fulfill the intended purpose

Dr. S.M.Mushtaque

RDD-Tirhut Division

Muzaffarpur

Introduction

1. Background

The health status of its population reflects the socio-economic development of a state. Health status is shaped by a variety of factors-level of income and standard of living, housing, sanitation, water supply, education, employment, health consciousness and personal hygiene, and the coverage, availability, accessibility, acceptability and affordability of health services. The poor health status of states is a product of inadequate nutrition, lack of protected water supply, and overcrowded and in sanitary housing conditions. These conditions are conducive to deficiency diseases, airborne diseases, focally related and waterborne diseases, which dominate the morbidity and mortality pattern in less developed regions.

The relationship between health and poverty or health and development is complex and multifaceted. Poverty in its various dimensions could be a manifestation as well as a determinant of an individual’s health. In its most basic form- as a state of food deprivation and nutritional inadequacy – poverty has a direct bearing on the morbidity and longevity of people. The other aspects of deprivation such as lack of access to critical amenities including safe water, sanitation, non-polluting domestic fuels, connectivity of life support services and, most importantly to education and general awareness, contribute to reinforcing ill health and morbidity, even leading to higher mortality levels. High child mortality levels on account of supervening infections, particularly diarrhoea and respiratory infections are fairly widespread among people deprived of these basic amenities of life. These commonly seen childhood infections often exacerbate malnourishment. Undernourishment in children in turn reinforces the consequences of such infections.

Health is a state of physical, mental & social well being & not merely an absence of disease or infirmity. Hence recognizing the importance of health in the process of economic & social development & improving the quality of life of our citizens, the Government of India has resolved to launch the National Rural Health Mission (NRHM) to carry out necessary architectural correction in the health care delivery system to achieve a positive health. The National Rural Health Mission (NRHM) seeks to provide effective health care to the entire rural population in the country with special focus on 18 states, which has weak public health indicators. It aims to undertake some architectural correction of the health system to enable it to be effective in providing “Health for All”. The mission envisages strategy for integrating ongoing vertical programs of health and family welfare, addressing issues related to the determinants of health like sanitation, nutrition and safe drinking water. The National Health Mission seeks to adopt sector wide approach and aims at systemic reforms to enable efficiency in health services delivery.

The NHM is an effort to bring about the architectural change to overall program management to enable rationalization of resources and simultaneously to augment then limited resources so that equity in health is ensured. The commonality of initiatives in the following areas would be complementing the similar efforts under NHM

NHM envisages “Attainment of Universal Access to Equitable, Affordable and Quality health care services, accountable and responsive to people’s needs, with effective inter-sectoral convergent action to address the wider social determinants of health”. To attain the above vision, NHM would seek to :

### Range and delivery of services

    - Prioritize achievement of universal coverage for Reproductive Maternal, Newborn, Child Health and Adolescents (RMNCH+A) services, National Disease Control and Non Communicable Diseases programmes in rural and urban areas.

    - Go beyond maternal and child survival to ensuring quality of life for women and children.

    - Expand focus from child survival to development of all children 0-18 years through a mix of delivery points and Community - Anganwadi and School (Govt. and Govt. aided) based health services and management at Secondary and tertiary facilities and especially District Early Intervention Centres.

    - Build an integrated network of all primary, secondary and a substantial part of tertiary care, providing a continuum from community level to the district hospital, with robust referral linkages to tertiary care and a particular focus on strengthening the Primary Health Care System including outreach services in urban slums.

    - Strengthening existing health care system to address the rising burden of Non-Communicable Diseases

    - Ensure that all public health care facilities or publicly financed private care facilities provide assured quality of health care services.

    - Converge with Department of Women & Child Development, Department of Education Ministry of Human Resource Development, Department of Tribal affairs, Department of Panchyati Raj Institutions and other related Department for effective manage  under-nutrition in children aged 0-3 years and anaemia among children, adolescents and women and provision of safe drinking water and sanitation.

### Equity

    - Plan for differential financial investments and technical support to states, districts and cities, with higher proportions of vulnerable population groups, including urban poor and destitute, and with difficult geographical terrain that face special challenges to meeting health goals.

    - Ensure increased access and utilization of quality health services to minimize disparity on account of gender, poverty, caste, other forms of social exclusion and geographical barriers.

    - Address shortages of skilled workers in remote, rural areas, urban slums, and other under-served pockets through appropriate monetary and non-monetary incentives.

    - Reduce out of pocket expenditure on health care, eliminate catastrophic health expenditures and provide social protection to the poor against the rising costs of health care, through cashless services delivered by public health care facilities, supplemented by contracted-in private sector facilities where-ever necessary.

### Health system strengthening

    - Support and supplement state efforts to undertake sector wide health system strengthening through the provision of financial and technical assistance; incentivize States to undertake health sector reforms that lead to greater efficiency and equity in health care delivery.

    - Improve Public Health Management by encouraging states to create public health cadre, and strengthening/ creating effective institutions for programme management, providing incentives for improved performance and building high quality research and knowledge management structures.

    - Support states to develop a comprehensive strategy for human resources in health, through policies to support improved recruitment, retention and motivation of health workers to serve in rural, remote tribal and underserved areas, improved workforce management, achievement of IPHS norms of human resource deployment, development of mid level care providers and creation of new cadres with appropriate skill sets, and in-service training.

    - Empower the ASHA to serve as a facilitator, mobilizer of community level care.

    - Ensure Quality Assurance for improved credibility of public health services.

    - Strengthen Health Management Information Systems as an effective instrument for programme planning and monitoring, supplemented by annual district level surveys and a strong disease surveillance system.

    - Ensure universal registration of births and deaths with adequate information on cause of death, to assist in health outcome measurements and health planning.

    - Create mechanisms to strengthen Behaviour Change Communication efforts for preventive and promotive health functions, action on social determinants and to reach the most marginalized.

    - Mainstream AYUSH, so as to enhance choice of services for users and learning from and revitalizing local health care traditions.

    - Develop effective partnerships with the not-for-profit, Non Governmental Organizations in all aspects of health care and with the for-profit, private sector to bring in additional capacity where needed to close gaps or improve quality of services.

    - Establish Accountability Frameworks at all levels for improved oversight of programme implementation and achievement of programme goals. The mechanisms for accountability shall range from participatory community processes like Jan Sunwais/Samwads, Social Audit through Gram Sabhas and professional independent concurrent evaluation.

    - Implement pilots for Universal Health Coverage (UHC) in selected districts in both EAG and non-EAG states to test approaches and innovations before scaling up.

### Program management

    - Continue to strengthen (1) Program management structures at state, Regional ,district, city, block and facility levels(2) Involvement of Panchayati Raj Institutions (PRIs) /Urban Local Bodies (ULBs) representatives in the governance and oversight of health services and (3) People’s organizations such as the Village Health Sanitation and Nutrition Committees (VHSNC) and Mahila Arogya Samitis (MAS) for convergent inter-sectoral planning and monitoring.

    - Build state, district and city capacity for decentralized outcome based planning and implementation, based on varying diseases burden scenarios, and using a differential financing approach. There will be a focus on results and performance based funding including linkage to caseloads.

    - Enable integrated facility development planning which would include infrastructure, human resources, drugs and supplies, quality assurance, and effective Rogi Kalyan Samitis (RKS).

    - Incentivize good performance of both facilities and providers.

2.Process of RHAP Preparation

A two day workshop organized by the State health society Bihar , on 26 th and 27th November 2013 , which has been attained by the all the Regional Programme Managers, Regional Accounts Manager,District Programme Managers and District Planning Coordinators . In this work shop all the concern State Programme Officers  briefs about their respective programmes and  the State Programme Manager and the two representatives of the  MSG strategic consulting Pvt. Ltd facilitate the workshop and clearing all the doubts of the participants .

A meeting was conducted at the divisional level under Chairmanship of RDD where all the components were discussed and all RPMU members taken active part in the preparation of the RHAP.

After a thorough situational analysis of district health scenarios in the division this document has been prepared. In the plan, it is addressing health care needs of rural poor especially women and children, the teams have analyzed the coverage of poor women and children with preventive and promotive interventions, barriers in access to health care and spread of human resources catering health needs in the division.

3.Profile of Tirhut Divsion

## History

Tirhut Division is one of the 9 divisions in Bihar. It contains 6 districts. Muzaffarpur District , Pashchim Champaran District , Purba Champaran District ,Sheohar District , Sitamarhi District , and Vaishali District are the districts in this division. Muzaffarpur Town is the headquarter of the division. The literacy rate is 42.37%. The female literacy rate is 29.43%. The male literacy rate is 53.99%.

The number of households in Tirhut is 2,887,357. Out of which rural household is 2,683,329 and the urban household is 204,028. 
Female to male ratio of Tirhut is 90.55%. Female to male ratio of the division is less than state's female to male ratio 91.93%. It is unsatisfactory and the people should drive some campaign to improve this. Urban female to male ratio of the division is 87.1% compared to rural female to male ratio of 90.84%.

The total working population is 40.72% of the total population. 60.77% of the men are working population . 18.38% of the women are working population. The main working population is 32.04% of the total population. 52.93% of the men are main working population . 8.78% of the women are main working population. While the marginal working population is 8.67% of the total population. 7.83% of the men are marginal working population. 9.6% of the women are marginal working population. The total non working population is 59.28% of the total population. 39.23% of the men are non working population. 81.62% of the women are non working population.

The literacy rate of the division is 42.37% compared to the literacy rate of state 47%. The literacy rate of the division is less than state literacy rate. The rate of literacy is very low and needs immediate attention of Union and State Government. . The female literacy rate is 29.43% compared to male literacy rate of 53.99%. The rural literacy rate is 40.11% compared to urban literacy rate of 68.43%. The rural female literacy rate is 26.91% compared to urban female literacy rate of 59.19%. The rural male literacy rate is 52.01% compared to urban male literacy rate of 76.39%.

4.Health facilities at a glance: Tirhut Division

| Total Health facilities |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Population (Cenus 2011) | Medical College and Hospital | DH | SDH | PHC | APHC | RH | HSC | Total Health Facility |
| Muzaffarpur | 4910213 | 1 | 1 | 0 | 16 | 79 | 1 | 488 | 586 |
| Sheohar | 674863 | 0 | 1 | 0 | 5 | 9 | 1 | 101 | 117 |
| Sitamarhi | 3513559 | 0 | 1 | 2 | 17 | 35 | 2 | 211 | 268 |
| Vaishali | 3595143 | 0 | 1 | 2 | 16 | 30 | 3 | 338 | 390 |
| East Chamaparan | 5230322 | 0 | 1 | 3 | 27 | 52 | 1 | 341 | 425 |
| West Chamaparan | 4036109 | 0 | 1 | 2 | 18 | 35 | 2 | 369 | 427 |
| Total | 21960209 | 1 | 6 | 9 | 99 | 240 | 10 | 1848 | 2213 |
|  |  |  |  |  |  | Source: DHIS 2 |  |  |  |

5. About RPMU

Regional Programme Management Unit

The Regional Programme Management Unit is formed under NRHM at the office of Regional Deputy Director – Health Services, and it provides Technical and Managerial Support to the District Health Societies in developing the Annual PIPs and district specific strategies for strengthening the National Programmes implemented at the District level under NRHM. The major activities done by RPMU are as follows:

- Facilitating the districts in smooth implementation of the Health programmes.

- Monitoring the progress of the district against the ELAs and ensure the work should be done as per the approved PIPs.

- Organizing Trainings and workshops at the Divisional level to enhance the capacity of the district and block level staff in order to refine their knowledge and update them regarding the recent developments and guidelines.

- Monthly Analysis of the HMIS data and FMR and regular feedback to the districts for improvements.

- Regular field visit of the health facilities by the RPMU staff for supportive supervision, findings of gaps, suggesting possible solutions and ensuring the corrective measures.

- Coordinating with the development partners and other stakeholders and building partnership with them for effective programme implementation.

- Capacity building of the front line workers during the district and block meetings for effective communication and proper community mobilization. This helps in improving their knowledge and their skills for proper counselling.

- Organizing the review meetings at the Divisional level where all the programmes were reviewed and follow up is done on instructions given during the meeting for ensuring the work as per the directions.

Organizational Structure:

6. Part A: FMR codes

Name of Program: …Administrative expenses………………..

FMR Code: ………A 1.4.3…………….

- Activity Proposed: - Administrative cost for JBSY

Background/Introduction (Project Description):- Janani Surksha Yojana is one of the successful schemes and it’s a huge programme. For the smooth implementation of programme administrative cost are required for awareness, review monitoring and social audit of the programme. As per the GOI guideline it should be 5 % of the total JSY budget. But seeing the expenditure of last year, this year we are proposing 2 % of total JSY budget. This will be incurred on monitoring & supervision through physical verification(Hiring of vehicle/Fuel) monthly review meeting , IEC , May Hire Data entry operator for computerizing data.

- Current Status & Situation Analysis: Physical verification of JBSY beneficiaries .

JSSK protocols displayed

Physical verification is being made on a very regular basis.

JSSK protocol displayed up to HSC level by RPMU.

- Goals:     Promote institutional delivery

Improvement of Maternal health

- Objective:

Awareness about the maternal health program.

Ensure timely Payment.

Proper implementation and monitoring of JBSY and JSSK

- Target :

Physical verification of 100 beneficiaries per quarter

- Strategies and activities proposed:

Monitoring of services

Physical verification of beneficiaries

IEC display

- Whether new or continued:

Continued

- Achievements (if the activity has been continued from previous year):

Improvement in maternal health

JSSK protocols displayed up to HSC and AWC level.

Ensured timely payment to beneficiaries.

9 . Justification:

For better program management and avoid any hitch with beneficiaries.

10.Deliverables :

Monitoring of all activities..

Timely payment of beneficiaries .

11. Fund Proposed :

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  | 4 | 75000 | 300000 | A1.4.3 |

Name of Program: …Orientation workshop, Dissemination of Manuals on MTP Services.

FMR Code: ……A.1.6.1……………….

Abortion is a significant medical and social problem worldwide.  It is estimated that half the abortions taking place around the world every year are performed outside authorized health services and or by unauthorized often unskilled providers and most take place in the developing world.  Whether spontaneous or induced, abortion has been a matter of concern over many decades now, particularly because of sepsis and other complications which lead to maternal morbidity and mortality.  In India, abortion is a major cause of maternal death and accounts for 8.9% of maternal mortality every year (RGI 1998).

- Current Status & Situation Analysis:

MTP is being done on demand by trained/ untrained practictioner

- Goals:

To Strengthen the  MTP Services at Facility level in Prevention and Management of Reproductive Tract Infection (RTI) and Sexually Transmitted Infections (STI).

- Objective:

Reduce incidence of unsafe abortion

Termination of early pregnancy with RU 486 and Misoprostol is offered to women under the purview of the MTP Act, 1971 and Rules 2003 which specify to whom, by whom and where pregnancy is to be terminated.

To update the knowledge of the Service provider and equipped them with current developments

To do the capacity building of the Service Provider.

- Target

Provision of MTP services on demand.

- Strategies Proposed:

Training (MVA Technology) of MOs and ANMs

- Activity Praposed :

One day manuals disseminations cum workshop on MTP

- Whether new or continued:

Continued

- Achievements (if the activity has been continued from previous year):

Workshop to be to be organised.

- Justification:

Refresher training required for MOs  and ANMs

- Deliverables:

MVA technology trained MOs and ANMs

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 1 | 1 | 80000 | 80000 | A1.6.1 |

Name of Program: …POL for Family Planning/Others (Including Additional Mobility Support).

FMR Code: ……A.3.3……………….

- Current Status & Situation Analysis:

Monitoring is being made of family planning activities and camps.

- Goals:

To Strengthen the Family Planning Services at Facility level.

- Objective:

- Regular monitoring of the family planning programme

- Ensuring quality family planning services at the facilities.

- Targets:

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |
| 12 | 12 | 12 | 12 |

- Strategies proposed:

Facilitation in monitoring and organizing family planning activities.

- Activity Proposed:

- Regular monitoring visits

- Conducting capacity building sessions at the facility level.

- Assessment of the facility for providing quality services as per the protocol.

- Whether new or continued:

Continued.

- Achievements (if the activity has been continued from previous year):

Regular monitoring and follow up is being made.

Improvement of family planning services.

- Justification:

Support in regular monitoring of the Programme

- Deliverables:

Increased performance of the districts against the ELAs

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  | 4 | 50000 | 200000 | A.3.3 |

Name of Program: …Monitor Progress and Quality, QAC Meetings/review of Sterilization.

FMR Code: ……A.3.5.1……………….

Background/Introduction (Project Description): Quality Assurance is an important Component of Family Planning .Through this dissemination of Guidelines and Contraceptive update is done among PHCs Medical officers and doctors who are conducting Minilap Tubectomy. Family Planning Review meeting is also done at district level.

- Current Status & Situation Analysis:

CS/ACMO/DPM/DCM/MOIC/BCM have been trained and review meeting completed.

- Goals:

To improve the quality of the services delivery in all facilities.

- Objective:

- To reduce the Death/Complication and Failure cases in Family Planning Programme.

- Ensuring quality family planning services in all facilities.

- Targets:

1 meeting.

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed:

Facilitation of activity in meetings.

- Activity Proposed:

- Organization of Monthly & Quarterly QAC meetings

- Assessment of the facility for providing quality services as per the protocols.

- Whether new or continued:

Continued

- Achievements (if the activity has been continued from previous year):

Meeting held

- Justification:

Facilitate in regular monitoring & improvement in the Programmes.

- Deliverables:

Improved quality service in all facilities.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  | 1 | 50000 | 50000 | A.3.5.1 |

Name of Program: …District Level Refresher Training of NBCC/LR Personnel.

FMR Code: ……A.9.3.7.3……………….

- Current Status & Situation Analysis:

Training is going on .

Equipments are being utilized.

- Goals:

To reduce the Early Neonatal Mortality Rate

- Objective:

- To ensure that every newborn should receive NBCC facility at the Facility.

- Proper utilization and Maintenance of NBCC equipment.

- Targets:

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |
| 1 | 1 | 1 | 1 |

- Strategies proposed:

Training of MOs/BHMs and ANMs

- Activity Proposed:

- Organization of District level training workshops.

- Refresher training to be organized.

- Whether new or continued:

Continued

- Achievements (if the activity has been continued from previous year):

87 facility trained

- Justification:

To facilitate in proper utilization and maintenance of NBCC equipments.

- Deliverables:

Refresher training for MOs/BHMs/ANMs/Sister nurses

Reduction in mortality and morbidity among newborn.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  |  | 20000 | 482850 | A.9.7.3 |

Name of Program: …IMEP Training for Medical Officer.

FMR Code: ……A.9.4.3……………….

- Current Status & Situation Analysis:

BMW activities that is segregation of BMW is being done at all facilities.

1 MO/1BHM/1SN/1 Safai Worker trained at divisional level.

- Goals: To reduce the mortality & morbidity related to Infection prevention

- Objective:

- To ensure the practice of IMEP guidelines at the facility

- To build the capacity of Medical Officers for implementation of IMEP guidelines.

- Targets:

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed:

Refresher training .

- Activity Proposed:

- Organization of Divisional level training of MO/SN/BHM/Safaikarmi.

- Whether new or continued: Continued

- Achievements (if the activity has been continued from previous year):Staffs are trained wastes are segregated.

- Justification: Improve the working conditions in the public health centres.

Refresher training is required.

- Deliverables: Reduction in mortality and morbidity related to infection prevention/

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  |  |  | 482850 |  |

Name of Program: …TOT on HBNC

FMR Code: ……A.9.5.3.1……………….

Ensuring that all newborns are provided with home based care through a series of home visits by ASHAs. Home based Newborn Care Operational Guidelines, 2011, published by GOI provides provide the schedule for home visits and relevant details for planning and monitoring of the scheme.  As per the HBNC guideline incentives are proposed for ASHAs. This is calculated as per the given formula ‘expected number of births in the state/district, with ‘Rs. 250’. All ASHAs are entitled for HBNC incentives irrespective of their training status in IMNCI or Module 6 & 7.

- Current Status & Situation Analysis:  HBNC TOT for Regional, District and block officials has been finished. Training of ASHA facilitators is being continued.

- Goals: To reduce the MMR & IMR

- Objective:

- To train the health staff on identification of the danger signs among Post partum mothers and newborn & timely referral.

- To build the capacity of front line workers for effective implementation of the programme.

- Targets:

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed & Activity Proposed:

- Organization of Divisional level refresher training as well review meeting of district and block officials.

- Whether new or continued: continued

- Achievements (if the activity has been continued from previous year): TOT of district level and block level officials are completed.

- Justification: Help in timely identification of danger signs among newborn and post partum mothers & timely referral.

- Deliverables: Increased number of Mothers  & newborn received proper care & timely referral.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
|  |  |  | 772610 | A9.5.3.1 |

Name of Program: …NSV Training of Medical Officers

FMR Code: ……A.9.6.3.2……………….

- Current Status & Situation Analysis:  Only 6 NSV trained doctors are available in the Division and the rate of Male sterilization is only 1 % of total sterilization.

- Goals: To increase the rate of  Male sterilization.

- Objective:

- To increase the number of Service provider conducting NSV

- Targets: 1 batch (2 MOs)

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed:  Organization of Divisional level training for 2 medical officers.

- Activity Proposed:

- Identification of Medical Officers for NSV training

- Ensure participation of doctors in the training.

- Whether new or continued: Continued

- Achievements (if the activity has been continued from previous year):

- Justification: Number of Service provider conducting NSV will increase which will help in increasing the rate of Male Sterilization in the division.

- Deliverables: Increased number of Male sterilization cases.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 26000 | 1 | 26000 | 26000 | A.9.6.3.2 |

Name of Program: …PPIUCD Insertion Training

FMR Code: ……A.9.6.3.2……………….

- Activity Proposed: Training of Medical officers in PPIUCD insertion

- Current Status & Situation Analysis:

3 batches of (3 MOs & 9 ANMs) has already been completed and they are doing the PPIUCD insertion at the facilites.

- Goals:

To increase the rate of PPIUCD insertion

- Objective:

- To increase the number of Service provider inserting PPIUCD

- Targets:

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |
| 1 | 1 | 1 | 1 |

- Strategies proposed:

- Organization of Divisional level training.

- Activity Proposed:

- Identification of facilities and participants for the training

- Coordination with SHSB for Master Trainers.

- Whether new or continued:

Continued

- Achievements (if the activity has been continued from previous year):

Training of 1 MO and 3 SN/ANMs from each facility. Total no. of batches 3 (12 facilities) are already covered.

- Justification:

Training of other MOs and SNs for PPIUCD insertion is highly required.

- Deliverables:

Increased number of Post Partum IUCD cases.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 63300 | 4 | 63300 | 253200 | A.9.6.7 |

Name of Program: …Training of RPMSU Staff.

FMR Code: ……A.9.8.4.1……………….

- Current Status & Situation Analysis:

Important activity as it is understood that the capacity building is continuous It is being proposed by the Training Cell, SHSB that the capacity building of the existing staff and new recruits/deputed staff at the Regional level will be an process. Under this activity, the existing RPMU officials/Staffs will undergo various trainings for the improved performance of the health programmes.

- Goals: To enhance the capacities and capabilities of RPMU Staff

- Objective:

- To update the knowledge of the RPMU and equipped them with current developments

- To do the capacity building of the RPMU Staff.

- Targets: 1

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed: Organization of training for RPMU staff

- Activity Proposed:

- Identification and nomination of interested candidates

- Selection and relieving of nominated candidates

- Whether new or continued: Continued

- Achievements (if the activity has been continued from previous year):

- Justification:

Since, the capacity building of health staffs is given emphasis in the NRHM, it is important to provide such opportunities to them. This will open the avenues for better exposure and learning, enhancing their skills and consequently improve the performance of health programmes. Training is also seen as not only a tool for the capacity building of the staffs but also inculcate ownership of programmes, job responsibilities etc. It helps the staff in understanding the programmes in different perspectives.

Since the RPMSU is newly established units in the state, the training to RPMSU staffs is must.

- Deliverables: To increased capacity of RPMU staff.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 50000 | 1 | 50000 | 50000 | A.9.8.4.1 |

Name of Program: …RPMU (RPM,RAM,RMEO,HMIS Supervisor, Office Assistant, BME,Radiation Safety Officer, Nursing Coordinator)

FMR Code: …A.10.4.2.………………….

- Current Status & Situation Analysis: The post of RPM/RAM/RMEO/BME/HMIS Supervisor/Office Assistant are in place and working as per the approved TOR. The Radiation Safety Officer/Nursing Coordinator will join after the selection and appointment from SHSB

- Goals: To strengthen the NHM activities in the division.

- Objective: To monitor the progress of the district against the ELA and ensure quality services to be delivered at the facilities.

- Targets: 1

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed: Coordination with DHS for smooth functioning and effective implantation.

- Activity Proposed:

1) Performance review of the district against the ELAs.

2) Monitoring visits to the health facilities and feedback to the district for improvement.

3) Timely compilation and submission of monthly reports to the SHSB.

- Whether new or continued: Continued

- Achievements (if the activity has been continued from previous year): Timely submission of reports and improvement in the health indicators of the district.

- Justification: RPMU is being established under NHM to closely monitor the performance of the districts and to do supportive supervision for smooth implementation of the programmes as per the approved PIPs.

- Deliverables: Improvement in the health indicators of the division.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 227000 | 1 | 227000 | 2724000 | A.10.4.2 |

Name of Program: …Mobility Support and office expenses to RPMU………………..

FMR Code: …A.10.7………………….

- Current Status & Situation Analysis: The fund is being utilized by RPMU for office expenses and for conducting Monitoring visits.

- Goals: To strengthen the National Health Programmes

- Objective: To monitor the implementation of the NHM activities in the districts under the division.

- Targets: 1

| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- |

- Strategies proposed: To develop the monthly Monitoring Plan by RPMU members.

- Activity Proposed:

- Conducting monitoring visits in the district and feedback to the districts for the improvement.

- Organization of Divisional Level review meeting.

- Participation in the DHS and SHSB meeting.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Regular field visits conducted and feedback given to the districts and uploaded at the SHSB website.

- Justification: Monitoring is an important component for the smooth and effective implementation of the programme.

- Deliverables: Improvement in the health indicators of the district.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 25000(Vehicle hiring/per month) + 50000 (Office expenses per month) | 1 | 75000 | 900000 | A.10.7 |

Part B: FMR Codes

Name of Program: HR at State Level.

FMR Code: …B.1.1.5.1………………….

- Current Status & Situation Analysis:  A post of Divisional ASHA Coordinator has been sanctioned in the RPMU which is in Place and monitoring the AHSA programme in the district.

- Goals: To Strengthren the ASHA programme.

- Objective:

- To monitor the performance of the ASHA programme in the district under the division.

- To coordinate the ASHA training programme in the district and do the follow up for performance improvement.

- Targets: 1 Post

- Strategies proposed: To do the regular monitoring of the ASHA programme and provide supportive supervision

- Activity Proposed:

- Monthly monitoring visits.

- Coordination with DCMs for smooth implementation of the programme.

- Analysis of district data and submission of reports to the SHSB.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Annexure Attached

- Justification: ASHA programme is an important component of NHM to for effective mobilization of the community to avail the services of the public health facilities. SO it is important to keep the position.

- Deliverables: Increased use of Public health services by the community.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 29700 | 1 | 29700 | 356400 | B.1.1.5.1 |

Name of Program: Mobility cost for ASHA Resource centre.

FMR Code: …B.1.1.5.4………………….

- Current Status & Situation Analysis:  The fund is utilized by Divisional ASHA coordinator for monthly monitoring visits and for office expenditure. The monitoring visit plan is attached for the reference.

- Goals: To Strengthen the ASHA programme.

- Objective:

- To monitor the performance of the ASHA programme in the district under the division.

- To coordinate the ASHA training programme in the district and do the follow up for performance improvement.

- Targets: Atelast 8 monitoring visit per month.

- Strategies proposed: To do the regular monitoring of the ASHA programme and provide supportive supervision

- Activity Proposed:

- Monthly monitoring visits.

- Coordination with DCMs for smooth implementation of the programme.

- Analysis of district data and submission of reports to the SHSB.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Annexure Attached

- Justification: ASHA programme is an important component of NHM to for effective mobilization of the community to avail the services of the public health facilities. SO it is important to keep the budget for mobility for regular monitoring of the programme..

- Deliverables: Increased use of Public health services by the community.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 10000(mobility) + 2000 (office expenses) | 1 | 12000 | 144000 | B.1.1.5.4 |

Name of Program: Convergence meeting with Health, PRIs, ICDS & PHED .

FMR Code: …B.8.2………………….

- Current Status & Situation Analysis:  VHSNC committees are formed in all the districts under the division and regular VHSND session are being planned. For effective coordination among different department a Divisional level meeting was conducted in the year 2012-13 and another meeting is proposed in the coming months.

- Goals: To increase the coordination among different departments for effective implantation of the programme at the community level..

- Objective:

- Capacity building of different stakeholders.

- To update their knowledge for smooth implantation of the programme

- To review the performance of the programme.

- Targets: 1

- Strategies proposed: To organize Divisional level meeting

- Activity Proposed:

- Ensure participation of representatives of different departments in the Divisional meetings.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Regular meetings of VHSNCs are conducted at the Village level and VHSND session are held every month as per the advance micro plan.

- Justification: Intersectoral convergence is required for the effective implantation of the health programme at the community level.

- Deliverables: Increased use of Public health services by the community.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 50000 | 2 | 50000 | 100000 | B.8.2 |

Name of Program: Training (Mainstreaming of AYUSH) .

FMR Code: …B.9.4………………….

- Current Status & Situation Analysis:

Traditional medicinal method Ayurvedic, Homeopathic and Unani to treat patients at  APHCs (50 % Ayurvedic, 30 % Homeopathic and 20% Unani doctors). From the ancient times the Ayurvedic method of medicine is used by the people for primary healthcare. Government is also trying to include Ayush method in primary healthcare facilities under the project collocation of Mainstreaming of Ayush. For this purpose Unani doctors are primarily posted at muslim dominated areas. Homeopathic doctors at Urban areas and Ayurvedic doctors can be posted at other places. At District hospitals Ayush Specialist doctor is to be posted to co-ordinate Ayush doctors posted at APHC level

.

- Goals: To strengthen the AYUSH programme

- Objective:

- Capacity building of AYUSH doctros.

- To update their knowledge for smooth implantation of the programme

- Targets: Six batches in a year.

- Strategies proposed: To organize Divisional level training for AYUSH doctors.

- Activity Proposed:

- To ensure the participation of all the doctors.

- To coordinate with the SHSB for availability of Master trainers.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Successful trainings was completed in the year 2012-13 and another training batch is proposed in the 4th quarter of the current F.Y.

- Justification: To meet up with the newly introduced methods and techniques in medical field it is proposed to train Ayush and allopathic doctors and other supporting staff at district, regional and State level and even outside state.

- Deliverables: Increased use of traditional method of Medicines by the community at the Public Health structure.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 720000 |  | 720000 | 720000 | B.9.4 |

Name of Program: Development of IEC/BCC strategy .

FMR Code: …B.10.1………………….

- Current Status & Situation Analysis:

The region, although, is showing progress on several development indicators, still is far below the desired levels especially on health indicators. Use of Social & Behavior Change Communication (SBCC) has been one of the key components in any health sector strategy. The poor status of health in the state is compounded by multiple factors such as access and quality of services on one hand and demand for health services and behaviors resulting from levels of knowledge, attitude and practices on the other hand. Influencing the practices and motivating the communities for adoption of health seeking behaviors is a challenge and needs to be addressed in a systematic manner. Behaviour change communication [BCC] is vital to bring about positive changes in the Health status of the women and children of the state.

Social Mobilization Van (Publicity van) is plays vital role in the community mobilization. This is the better medium to create enable environment for the demand of service availability. Initially it is starts in the division level and after that according to the feedback and evaluation basis extended in district level.

Role of the van is creating awareness about national flagship and state health programs among the rural and urban community and increase the health service demand. Mid media activity conducted through this van.

.

- Goals: To increase the knowledge level of the Community and to bring the behavior change.

- Objective:

- To provide the specific information to the community on different health programmes and healthy behaviors.

- To increase the knowledge level of the community

- Targets: 1 IEC Van/ 1 Hoarding per district

- Strategies proposed: To increase the awareness through IEV van and Hordings.

- Activity Proposed:

- To prepare the district wise route plan for the IEC van

- Display of hoardings at proper places in the district headquarter.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): IEC van is showing 6 shows every day at different places as per the advance route plan prepared for them.

- Justification:

Strategic approach to communication is imperative to improve effectiveness and sustainability of behavior and social change. A systematically developed and managed communication program supported by evidence-based strategies, state-of-the-art training and capacity building, and cutting-edge research is necessary to influence positive behaviors & practices as also to increase access, improve quality & promote demand for health services.

- Deliverables: Increased knowledge level of the community regarding different health programmes.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 1838144 |  | 1838144 | 1838144 | B.10.1 |

Name of Program: Mobile Medical Unit (Dhanvantri Rath).

FMR Code: …B.11.1.2………………….

- Current Status & Situation Analysis:

## SHS, Bihar on behalf of the Department of Health, Government of Bihar invited Private Service Providers for providing Mobile Medical Units (each unit fitted with GPS- Global Positioning System) to provide primary health care facilities in the hard to reach rural areas of various districts of Bihar.

- Goals

To provide and supplement primary health care services for the far flung areas (especially for Maha Dalit Tolas)  in the various districts of Division .

- Objective:

To provide and supplement regular, accessible and quality primary health care services for the farthest areas in the districts of Bihar and to provide visible face for the mission and the Government, also establishing the concept of Healthy Living among the rural mass

- Targets: 1 MMU (Dhanvantri Rath)

- Strategies proposed:

- Activity Proposed:

- Preparation of rote plan for the MMU.

- Ensuring Quality Standards

- Providing detailed reports and maintain database of information of MMU services as per the Performas provided at the time of signing of the contract, or as issued by the SHS from time to time.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): IEC van is showing 6 shows every day at different places as per the advance route plan prepared for them.

- Justification: To continue provision of primary health care facilities in hard to reach rural areas of all districts of Bihar.

.

- Deliverables: Atleast 50 patients are seen daily and investigations are being done as per the requirements.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 300000 | 1 | 300000 | 3600000 | B.11.1.2 |

Name of Program: Regional Quality Assurance Committee meeting.

FMR Code: …B.15.2.4.1

- Current Status & Situation Analysis:

## One  RQAC meeting was held in the current F.Y. and 2 more meetings are proposed in the 3rd & 4th Quarter of the current F.Y.

- Goals:

To improve the quality standards of the Public Health facilities.

- Objective:  To strengthen the identified centers for FFHI accreditation.

- Targets: 4 meeting (1 each quarter)

- Strategies proposed: To organize the RQAC meeting at the divisional level

- Activity Proposed:

- Review of the DQACs meeting and to monitor the progress.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): All DQACs are formed and conducting the regular monthly DQAC meeting.

- Justification: Important for ensuring the quality standard at the facility level.

.

- Deliverables: 1 Facility is in the process of final certification and work is continued at other identified centres..

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 5000 | 4 | 5000 | 20000 | B.15.2.4.1 |

Name of Program: Quality Assurance in facility based MNCH (QA-MNCH (FBNC+ labor room) through mechanism of supportive supervision and mentoring..

FMR Code: …B.15.2.5.3

- Current Status & Situation Analysis:

Quarterly monitoring of NBCC/Labor room is done at the facility level through RPMU/ DHS members. 2 round of visits has been conducted in the current F.Y.

- Goals:

To Reduce the MMR & IMR in the districts.

- Objective:

To ensure the standard protocols at the Labor room and NBCC.

- Targets: 2 visit rounds per year.

- Strategies proposed: Formation of Monitoring Team and preparation of Monitoring Plan

- Activity Proposed:

- Monitoring visits as per the prepared plan.

- Submission of reports to the SHSB and concerned district.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): 2 round of Monitoring visits are completed in the current F.Y.

- Justification: Monitoring is required for facility strengthening and smooth functioning of the NBCCs and Labor romm

.

- Deliverables: All NBCCs /SNCUs (1) are functional in the division.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 225000 | 2 | 225000 | 450000 | B.15.2.5.3. |

Name of Program: Divisional Data Centre

FMR Code: …B.15.3.3.10.2

- Current Status & Situation Analysis:

The divisional data centre is functional at the Divisional level and 5 data operators are appointed through the outsourcing agency for providing support in preparation of district wise reports and for regular office work.

- Goals:

For smooth implementation of NHM at Divisional level.

- Objective:

Timely submission of Monthly reports and monitoring of programmes through reports.

- Targets: 1

- Strategies proposed: To ensure the daily reporting from the health facilities.

- Activity Proposed:

- Collection of daily reports and Doctors attendance.

- Submission of concise reports to the RPMU.

- Fax and email of official letters to the concerned officers.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Daily collection of reports.

- Justification: Require for strong monitoring mechanism.

.

- Deliverables: Timely submission of reports.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 59000 | 1 | 59000 | 708000 | B.15.3.3.10.2 |

Name of Program: Data Centre at the office of Divisional Commissioner

FMR Code: …B.15.3.3.10.5

- Current Status & Situation Analysis:

1 data operator is posted at the office Divisional Commissioner to assist in the compilation of Reports from the District health department.

- Goals:

For smooth implementation of NHM at Divisional level.

- Objective:

Timely submission of Monthly reports and monitoring of programmes through reports.

- Targets: 1

- Strategies proposed: To ensure the monthly reporting from the health facilities.

- Activity Proposed:

- Submission of concise reports to the Divisional Commissioner.

- Fax and email of official letters to the concerned officers.

- Whether new or continued: Continued.

- Achievements (if the activity has been continued from previous year): Monthly collection of reports.

- Justification: Require for strong monitoring mechanism.

.

- Deliverables: Timely submission of reports.

- Funding proposed:

| Unit of Measure | No of units | Cost per Unit | Total Cost | FMR Code |
| --- | --- | --- | --- | --- |
| 16500 | 1 | 16500 | 198000 | B.15.3.3.10.5 |

NHM Framework for Implementation, Version 5.2, Draft, August 7, 2013